## Sheet1
PP4 Project plan
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Blog | Authetication | bar: 9
User Stories | Blog | bar: 13
User Stories | Booking | bar: 13
User Stories | Contact | bar: 13
User Stories | General | bar: 13
User Stories | User Panel | bar: 13
Docs | Check project docs to confirm all areas are covered | bar: 13
Blog | Refine comments and detail views | bar: 14
Blog | Add likes functionality | bar: 14
Blog | Link recent blogs to homepage | bar: 15
Blog | Tidy Blog views | bar: 15
General | User panel creation | bar: 16
General | Sam to design Images | bar: 14 to 17; 20 to 24
Book | Create model | bar: 17
Book | Create view that shows 4 options | bar: 17
Book | Add button to book sessions | bar: 20
Book | Select date and time for session and confirm | bar: 20
Book | Add booking to user panel | bar: 21
Contact me | Design simple contact form with map and details | bar: 22
Contact me | Add Js verification | bar: 22
Contact me | email form and show confirmation message | bar: 22
Mobile | Fix any issues with responsivness | bar: 23
Test | Create tests for views and models as required | bar: 24
Test | use usual online tools to verify code | bar: 24
Readme | Create readme | bar: 27
Optional
Shop | if time allows | bar: 28 to 31