## gant
PP4 Project plan
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Blog | Authetication | bar: 9
User Stories | Blog | bar: 13
User Stories | Booking | bar: 13
User Stories | Contact | bar: 13
User Stories | General | bar: 13
User Stories | User Panel | bar: 13
Docs | Check project docs to confirm all areas are covered | bar: 13
Blog | Refine comments and detail views | bar: 14
Blog | Add likes functionality | bar: 14
Blog | Link recent blogs to homepage | bar: 15
Blog | Tidy Blog views | bar: 15
General | User panel creation | bar: 16
General | Sam to design Images | bar: 14 to 17; 20 to 24
Book | Create model | bar: 17
Book | Create view that shows 4 options | bar: 17
Book | Add button to book sessions | bar: 20
Book | Select date and time for session and confirm | bar: 20
Book | Add booking to user panel | bar: 21
Contact me | Design simple contact form with map and details | bar: 22
Contact me | Add Js verification | bar: 22
Contact me | email form and show confirmation message | bar: 22
Mobile | Fix any issues with responsivness | bar: 23
Test | Create tests for views and models as required | bar: 24
Test | use usual online tools to verify code | bar: 24
Readme | Create readme | bar: 27
Optional
Shop | if time allows | bar: 28 to 31

## user stories
|  | As a | USER | As a | ADMIN
|  | I can | so that I can | I can | so that I
Modules
Welcome | 1 | Easily Navigate to the section I want | select the page I need to interact with
| 2 | View recently created content | see new blog posts that may interest me
| 3 | See available sessions and how to book them | arrange to train with the site owner
| 4 | Conatct the site owner | ask questions or request further information
| 5 | View contact information and the location of services | find out where sessions take place
| 6 | Link to the users social media accounts | follow the site owner across avaialble platforms
| 7 | Create an account and sign in/out of the account | book sessions
Blog | 8 | View a list of all blogs | select what I want to learn about | Manage posts: As a Site Admin I can create, read, update and delete posts so that I can manage my blog content
| 9 | Access the detailed content of the blog | find out about the subject of the blog | Create drafts: As a Site Admin I can create draft posts so that I can finish writing the content later
| 10 | Comment on a post | ask questions, make comments or respond to other comments | Approve comments: As a Site Admin I can approve or disapprove comments so that I can filter out objectionable comments
| 11 | Like a post | show my appreciation for blog posts I like
Booking | 12 | See available sessions | help me make a selection about what I want to book
| 13 | Book sessions | arrange a session at a time that suits me
Contact | 14 | Complete a contact form | ask questions or ask for further information
Account Page | 15 | View my profile | check my details are correct
| 16 | Review bookings I have made | see what I have booked with the trainer
| 17 | Change bookings I have made | remove bookings that I cannot attend